## Instructions
Multi-Client Month-End Close Tracker
For accounting firms running month-end close across many clients at once.
How it works
1. On the Clients sheet, list every client you close each month in the yellow input cells: entity count, accounting software, the close owner at your firm, and the target number of days to close.
2. On the Close Tracker sheet, add one row per client per task. Pick the Client, Task, and Status from the dropdowns, then enter the Due Date and, once finished, the Completed Date.
3. Days Late computes automatically: if a task was completed after its due date, it shows how many days late; otherwise 0. It stays blank until both dates are filled.
4. The Summary sheet rolls everything up per client with formulas only: total tasks, tasks done, percent complete, blocked count, days to close so far, and how that compares with the client's target. A firm-level totals row sits at the bottom.
Monthly workflow
At the start of each month, right-click the Close Tracker tab and choose Move or Copy > Create a copy. Rename the copy for the new period (for example, Close Tracker Jul), clear the Completed Date and reset Status to Not started, and update the Due Dates. The Summary formulas read the sheet named Close Tracker, so keep the current month on that tab and archive old copies.
Conventions
Yellow cells are inputs; everything else computes from them. Never type over a formula cell.
Statuses drive all rollups: only rows marked Done count as complete, and Blocked rows surface in the Summary blocked count so partners can unstick them fast.
Days to close so far = latest completed date minus earliest due date for that client, an honest elapsed-days measure of how long the close has been running.
Worked example
The workbook ships with six sample clients and 31 tasks for a June close. Delta Property Group is fully delivered (6 of 6 done, closed in 8 days against an 8-day target), while Cedar & Vine has two blocked tasks dragging its close. Replace the sample rows with your own clients and tasks.

## Clients
Client | Entity Count | Software | Close Owner | Target Days to Close
Acme Robotics | 1 | QuickBooks Online | Priya S. | 5
Bluebird Dental | 2 | Xero | Marcus T. | 7
Cedar & Vine Restaurants | 3 | QuickBooks Online | Priya S. | 10
Delta Property Group | 4 | QuickBooks Desktop | Jordan K. | 8
Everline SaaS | 1 | NetSuite | Marcus T. | 5
Foster Community Fund | 1 | QuickBooks Online | Jordan K. | 12

## Close Tracker
Client | Task | Owner | Due Date | Completed Date | Status | Days Late
Acme Robotics | Bank rec | Priya S. | 2026-07-02 | 2026-07-02 | Done
Acme Robotics | Credit cards | Priya S. | 2026-07-02 | 2026-07-03 | Done
Acme Robotics | Accruals | Priya S. | 2026-07-03 | 2026-07-03 | Done
Acme Robotics | Financials draft | Priya S. | 2026-07-05 |  | In progress
Acme Robotics | Partner review | Dana R. | 2026-07-06 |  | Not started
Bluebird Dental | Bank rec | Marcus T. | 2026-07-03 | 2026-07-02 | Done
Bluebird Dental | AR review | Marcus T. | 2026-07-04 | 2026-07-06 | Done
Bluebird Dental | AP cutoff | Marcus T. | 2026-07-04 |  | Blocked
Bluebird Dental | Payroll tie-out | Sam W. | 2026-07-05 | 2026-07-05 | Done
Bluebird Dental | Financials draft | Marcus T. | 2026-07-08 |  | Not started
Cedar & Vine Restaurants | Bank rec | Priya S. | 2026-07-03 | 2026-07-05 | Done
Cedar & Vine Restaurants | Credit cards | Priya S. | 2026-07-03 | 2026-07-05 | Done
Cedar & Vine Restaurants | AP cutoff | Sam W. | 2026-07-05 |  | Blocked
Cedar & Vine Restaurants | Accruals | Priya S. | 2026-07-06 |  | In progress
Cedar & Vine Restaurants | Payroll tie-out | Sam W. | 2026-07-06 |  | Blocked
Cedar & Vine Restaurants | Financials draft | Priya S. | 2026-07-09 |  | Not started
Delta Property Group | Bank rec | Jordan K. | 2026-07-02 | 2026-07-02 | Done
Delta Property Group | AR review | Jordan K. | 2026-07-05 | 2026-07-04 | Done
Delta Property Group | Accruals | Jordan K. | 2026-07-06 | 2026-07-07 | Done
Delta Property Group | Financials draft | Jordan K. | 2026-07-08 | 2026-07-08 | Done
Delta Property Group | Partner review | Dana R. | 2026-07-09 | 2026-07-10 | Done
Delta Property Group | Delivered | Jordan K. | 2026-07-10 | 2026-07-10 | Done
Everline SaaS | Bank rec | Marcus T. | 2026-07-02 | 2026-07-02 | Done
Everline SaaS | Credit cards | Marcus T. | 2026-07-02 | 2026-07-02 | Done
Everline SaaS | Payroll tie-out | Sam W. | 2026-07-03 | 2026-07-03 | Done
Everline SaaS | Accruals | Marcus T. | 2026-07-03 | 2026-07-04 | Done
Everline SaaS | Financials draft | Marcus T. | 2026-07-05 |  | In progress
Foster Community Fund | Bank rec | Jordan K. | 2026-07-05 |  | In progress
Foster Community Fund | AR review | Jordan K. | 2026-07-06 |  | Not started
Foster Community Fund | Accruals | Jordan K. | 2026-07-08 |  | Not started
Foster Community Fund | Financials draft | Jordan K. | 2026-07-12 |  | Not started

## Summary
Client | Target Days | Tasks Total | Done | % Complete | Blocked | Days to Close So Far | Vs Target (days)
Firm total