## Instructions
Construction WIP Schedule (Over/Under Billing)
A work in progress (WIP) schedule reports every open job under the percentage-of-completion method: revenue is earned in proportion to costs incurred, not in proportion to what has been billed. It is the report sureties, bonding agents, and lenders ask for because it reveals whether a contractor is billing ahead of the work (over billed) or funding work out of pocket (under billed).
How to use this template
1. Go to the WIP Schedule sheet. Enter one row per open job in the light yellow input cells only: Job #, Job Name, Contract Value, Approved Change Orders, Estimated Total Cost, Cost to Date, and Billed to Date.
2. Every white column computes automatically. Never type over a formula cell.
3. Add more jobs by inserting rows above the TOTALS row and copying the formulas down.
4. Six sample jobs are prefilled so you can see how the schedule behaves. Replace them with your own jobs.
Worked example
Job 2401 has a $2,450,000 contract plus $125,000 of approved change orders, so the revised contract is $2,575,000. Costs to date of $1,554,000 against an estimated total cost of $2,220,000 put the job at 70.0% complete, which earns $1,802,500 of revenue. Because the contractor has billed $1,890,000, the job is over billed by $87,500.
What each computed column means
Revised Contract | Contract Value plus Approved Change Orders; the current full contract amount.
% Complete | Cost to Date divided by Estimated Total Cost (cost-to-cost method); zero until an estimate is entered.
Earned Revenue | % Complete multiplied by Revised Contract; the revenue recognized to date.
Over Billing | Billed to Date minus Earned Revenue when positive; billings in excess of earned revenue.
Under Billing | Earned Revenue minus Billed to Date when positive; costs and earnings in excess of billings.
Estimated Gross Profit | Revised Contract minus Estimated Total Cost; the profit expected at completion.
Gross Profit % | Estimated Gross Profit divided by Revised Contract.
Reading over and under billings
Over billing (billings in excess of costs and estimated earnings) is a LIABILITY on the balance sheet: cash has been collected ahead of the work. Under billing (costs and estimated earnings in excess of billings) is an ASSET: work is done but not yet billed. A job can only be one or the other, so exactly one of the two columns is zero on every row. Large or aging under billings are the first thing a surety will question.

## WIP Schedule
Job # | Job Name | Contract Value | Approved Change Orders | Revised Contract | Estimated Total Cost | Cost to Date | Billed to Date | % Complete | Earned Revenue | Over Billing | Under Billing | Estimated Gross Profit | Gross Profit %
2401 | Riverside Office Park | 2450000 | 125000 |  | 2220000 | 1554000 | 1890000
2402 | Maple Street Apartments | 3800000 | 0 |  | 3420000 | 1197000 | 1150000
2403 | Highway 12 Bridge Repair | 1275000 | 85000 |  | 1150000 | 1092500 | 1320000
2404 | Cedar Grove Clinic | 940000 | 40000 |  | 855000 | 427500 | 410000
2405 | Northside Warehouse Expansion | 1680000 | -60000 |  | 1510000 | 604000 | 720000
2406 | Elm School Gymnasium | 2150000 | 95000 |  | 1995000 | 399000 | 350000
TOTALS